## Slide 1
Katrina Krivenko
Executive project manager
On-board implementation of the multi-purpose
Event Timer (MPET)

## Slide 2: Company overview
Founded in 2011
Spin-off from Institute of Electronics and Computer Sciences
First technology licensing in LV
2-3 ps accuracy = sub cm spatial accuracy
55 Event Timers sold
50% of Satellite Laser Ranging market

## Slide 3: Project overview
Kick-off meeting: 01.02.2016
Duration: 31.12.2017 (23 months)
Contract price: 396,038 EUR
Project executed by:
  Eventech (LV, Prime Contractor)
  Institute of Electronics and Computer Science (LV)
  Czech Space Research Centre (CZ)

## Slide 4: Project goal
Creation of an innovative, competitive on the world market, multi-purpose Event Timer (MPET) for Space related applications, which is hardened against radiation, wide-range temperatures, vibrations and shocks that may occur in the space environment.

## Slide 5: Deliverables
Hardware
  BB / Breadboards 1 and 2
  EM / Engineering Model
  QM / Qualification Model
Documentation package

## Slide 6: Accomplished
Onboard Event Timer module detailed specifications (SRR)
Design documentation, assembled and tested Breadboard 1 (Milestone 1)
Design documentation for Breadboard 2 (PDR)

## Slide 7: Challenges
the European Cooperation for Space Standardization (ECSS)
Electronic component procurement
  Very poor choice of high-speed active components
  High MOQ’s → pricing exceeds budget
  Testing limitations for engineering level components
  Leads to many design changes
Industrial partner finding

## Slide 8: Lessons learned
Planning and design as detailed as possible before project implementation
Good contact with electronic component distributors and pricing info
Keep close contact with ESA Technical officer and assigned project experts
Timely risk detection and mitigation

## Slide 9: Recommendations
Trustworthy and ESA experienced partners with space heritage
Additional expertise
Advanced planning
Risk management
Know how-to work with ESA
New partner search

## Slide 10: Future plans and perspectives
Next projects with ESA
  Space-related terrestrial hardware project with Austrian partners
  Space hardware project with German and Czech partners
  Industrial partner search for FM development

## Slide 11: Thank you for attention!
CONTACTS
SIA Eventech
Ms. Katrina Krivenko
Executive project manager
+371 2911 8068
katrina@eventechsite.com
eventechsite.com